Introduction to Software Engineering

Weekly Status Report

The student team is required to complete the Weekly Status Report documentation for the assigned course project, following the attached template.

Software Engineering Department

Faculty of Information and Technology

University of Science

Table of Contents

Objectives	1
1 Submission	2
2 Report Information	3
2.1 Task Status	3
2.2 Plan for Next Week	4
2.3 Issues and Risks	4
2.4 Meeting Minutes	5
2.5 Metrics	5

Weekly Status Report

# Objectives

This document focus on the following topics:

- Reporting weekly progress against the project plan

- Recording issues and risks

- Recording the weekly status meeting

# Submission

- One report per week, from week 2 to week 10 (9 reports). The team lead (or backup) is responsible.

- The team chooses its own weekly deadline (e.g., the day after the status meeting) and states it in PA1.

- Commit the report to the repository: /docs/management/weekly/W<week>-status.docx (or .md), e.g., W03-status.docx. Do not overwrite or rewrite earlier reports; the commit history is the evidence of timeliness.

- Reports are not submitted on Moodle. They are graded at the end of the course as part of the Teamwork & tool usage component (working process).

# Report Information

| Item | Value |
| --- | --- |
| Team | DiDung – Team 10 |
| Week | 4 (19–25/10/2026) |
| Date of meeting | Tuesday, 20 Oct 2026, 09:00 (DID-15; all four present). Separate offline meeting: Tue 27 Oct (W5). |
| Current phase / PA | PA2 – Software Requirements Specification; scope review, initial UI/backend feasibility and technical preparation. |
| Prepared by | Vo Dinh Cao Minh Hao (Hào) – Tester; weekly report owner |
| Overall status | AMBER — PA2 requirements baseline and independent review are pending. Prototype/template discussed in W5; flood/tidal forecasting is under feasibility investigation, not approved for deployment. |

## Task Status

W4 reporting period: 19–25 Oct 2026 (ICT). This section includes only PA2-relevant work. PA2 Epic DID-21 was To Do at the W4 cutoff; PA2 SRS sub-tasks DID-40–58 were created on 27 Oct (W5) and must not be counted as completed in W4. Early technical work supports future PA2 design decisions but does not constitute an approved SRS or validated prototype.

| WBS / task | Owner | Planned finish | Status | % done | Notes |
| --- | --- | --- | --- | --- | --- |
| DID-21 — PA2 Requirements & SRS | Hiếu (PM), Tiến (BA) | 3 Nov (updated deadline) | To Do (W4) | 75 | PA2 Epic opened 18 Oct; requirements baseline, FR/NFR, use cases and review not yet signed off at W4 close. |
| PA2 feasibility — prototype / UX direction | Đạt / team | W5 planning | Planning (W4) | 75 | W4 design/landing assets and interface preparation exist. Team confirmed shared template, Figma and prototype coverage at offline meeting 27 Oct (W5), not W4. |
| PA2 technical feasibility — data/API architecture | Hiếu / Tiến | W4 exploration | Exploration (W4) | 100 | Backend/schema/API development evidenced by DID-37 and PR #7/#8; these support SRS feasibility but do not establish a reviewed requirements baseline. |
| PA2 scope — flood/tide forecasts and source research | Tiến / Hiếu | W5 review | Open question | 20 | Potential use of permitted Facebook posts to infer flood/tidal signals discussed 27 Oct (W5). No validated dataset, model, or go/no-go result confirmed. |

## Plan for Next Week

| WBS / task | Owner | Planned finish |
| --- | --- | --- |
| DID-40/43: Confirm PA2 scope and feasible data sources; evaluate whether permitted public Facebook reports can support flood/tide signals, including bias, locations, timestamps and privacy. | Tiến / Hiếu | 29–31 Oct |
| DID-48/50/51/52: Map Must-have FR/UC to screen inventory and responsive Figma wireframes/prototype; check accessibility, loading/stale/error states. | Đạt / BA review | 30 Oct–1 Nov |
| DID-44–47/49: Complete FR/NFR/business rules, acceptance criteria and ≥6 Must-have use-case specifications. | Tiến / Hiếu / Hào | 31 Oct–1 Nov |
| Assess feasibility of flood/tide forecasting: lawful data access, label validity, representative samples, independent baseline and go/no-go criteria; no feature promotion before approval. | Hiếu / Tiến | By 1 Nov |
| Agree system architecture: Next.js UI/API, Supabase schema/auth, ingestion scheduler, data adapters and Figma-to-code contract; begin initial development tasks. | Hiếu / Tiến / Đạt | By 2 Nov |
| DID-53/54: Finish RTM and independent requirements review; document findings, owners, fixes and remaining risks. | Hào / peers | 2 Nov |
| DID-57/58: Integrate PA2 SRS, final DOCX/PDF, review PR, confirm Moodle rules and submit with receipt. | Hiếu / Team | 3 Nov |
| PA2 final review and delivery: DID-57/58 by 3 Nov; W4 report DID-59 is supporting process evidence, not PA2 deliverable. | Hiếu / Hào | 3 Nov PA2; W4 report 28 Oct |

## Issues and Risks

| ID | Description | Impact | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| I1 | PA2 scope remains unresolved: PA0 flood/tide features vs AQI-centered MVP. Team exploring options, without TA acceptance on record. | Unresolved scope could affect FR and architecture. | Map PA0 Must-haves; document PM/TA approval or Pending before SRS baseline. | Tiến / Hiếu | Before 3 Nov |
| I2 | Facebook flood/tidal posts remain exploratory. Data access, licensing, privacy, event time/location and sampling bias are unknown. | Unreliable training labels and misleading predictions. | Use permitted sources only; avoid personal data and validate signals against official hydrological observations. | Hiếu / Tiến | 1 Nov |
| R1 | PA2 prototype is team-reported as covering Must-haves after 27 Oct; SRS traceability and independent review still pending. | Potential mismatch between SRS and implementation. | Trace Figma to FR/UC, clarify API contract, run actual functional tests and log evidence. | Đạt / Hào / Hiếu | 2 Nov |
| R2 | PA2 review trail incomplete. GitHub PR approvals refer to development workflow, not approval of PA2 SRS. | Review trail incomplete. | Record peer reviewer, comments, test evidence and decision on each future PR. | Hiếu / Hào | Before PA2 PR |
| I3 | PA2 is due on 3 Nov; RTM, use cases, prototype and review have little handoff time. | Potential missed milestone/rework. | Review each section, resolve blocking issues, log final approval and actual submission. | Hiếu / Tiến | 3 Nov |

## Meeting Minutes

| Member | Present | Done since last meeting | Next | Blockers |
| --- | --- | --- | --- | --- |
| Truong Le Trung Hieu | Yes | PA2 coordination and technical stack preparation; no completed PA2 SRS deliverable recorded by W4 close. | Review PA2 scope, system architecture and deliverables. | Awaiting scope/TA decision. |
| Tran Minh Tien | Yes | Backend/API feasibility work supports PA2 requirements; no signed-off FR/BR baseline in W4. | Write FR and assess feasibility of source data. | Provider coverage, data quality. |
| Nguyen Thanh Dat | Yes | Initial UI/landing design work; template/prototype agreement confirmed at 27 Oct W5 meeting. | Prepare UC diagram, Figma screens and user flows. | Must-have baseline not frozen. |
| Vo Dinh Cao Minh Hao | Yes | Planning for PA2 acceptance criteria, RTM and independent requirements review; no completed PA2 QA evidence at W4 cutoff. | Write AC, RTM, SRS review and Login test. | Test environment/review proof pending. |
| W5 meeting (27 Oct) | All four | Offline: agreed UI template and Figma; prototype reportedly covers Must-have screens; researching Facebook flood/tide signals. | Evaluate forecast feasibility; agree architecture and initial code plan. | Meeting minutes and Figma URL pending. |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 0 completed PA2 SRS task closures verified in W4. PA2 Epic DID-21 remained To Do. | 0 PA2 SRS task closures by W4 cutoff; sub-tasks DID-40–58 created W5. |
| Commits | Repository-wide: 27 commits in W4, including PA2-supporting UI/API work; not attributable wholly to PA2. | Repository-wide: 34 main commits through 25 Oct; PA2-only count unverified. |
| Pull requests merged / reviewed | Repository-wide: 7 PRs merged in W4; PA2 SRS review PR not verified. | 0 verified PA2 SRS PR approvals at W4 cutoff. |
| Open defects (PA5) | PA2 acceptance/requirements test outcomes not available in W4. | Not measured; no PA2 SRS test baseline. |
| CI workflow runs | Repository-wide: 7 successful CI workflow runs in W4 (supporting development only). | PA2 SRS validation is not established by CI success. |